## StoryMapping
[8 empty] | Check last updates in: | https://github.com/h3afif/ScrumProjectsPlan
[7 empty] | STORIES, TASKS / RELEASE |  |  |  |  | Not started | 2 | 7.407% | Progress subset% all% | 4 | 0
[12 empty] | In progress | 14 | 51.85% | Progress | 15 | 0
[12 empty] | Closed | 7 | 25.93% | Progress | 9 | 0
|  |  |  | Current | [7 empty] | Applied | 2 | 7.407% | 36% | 5 | 0
|  |  |  | Week 201725 | [7 empty] | Canceled | 2 | 7.407% |  | 2 | 0
[12 empty] | Suspended | 0 | 0% | 42.42% | 0 | 0
[12 empty] | N/A | 0 | 0% |  | 0 | 0
Target Week | Week of closure or appling | Processed O/N | To be counted | Target Sprint / Week |  | Ref | Type / Module | Story Description | Feature/Project | Priorité | Points | Target Date | Date reviewed | Status | Closure or Applied Date | Task/Comment | Team/Contact | LOG
201713 | 201713 | Y | 1 | 201713 |  | A1 | US | Story 1 description | Feature 1 |  | 5 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201713 | 201715 |  | 0 | 201713 |  | A2 | Spike | Story 2 description | Feature 1 | 1 | 8 | 2017-03-30 |  | Canceled | 2017-04-13 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 1 | + Status changed to 'In progress' (@ 13/04/2017) + Status changed to 'N/A' (@ 13/04/2017) + Status changed to 'Suspended' (@ 13/04/2017) + Status changed to 'Not started' (@ 13/04/2017) + Status changed to 'In progress' (@ 13/04/2017)
201719 | 201716 | Y | 1 | 201719 |  | A3 | Spike | Story 3 description | Feature 2 |  | 2 | 2017-05-12 |  | Closed | 2017-04-16 | + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Closed' (@ 4/16/2017) ¦
201713 | 201715 | Y | 1 | 201707 |  | A4 | Spike | Story 4 description | Feature 2 |  | 40 | 2017-03-30 | 2017-02-17 | Closed | 2017-04-13 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Closed' (@ 4/17/2017) ¦ + New reviewed date: '2/17/2017' (@ 4/17/2017) ¦ + New reviewed date: '5/17/2017' (@ 4/17/2017) ¦ + New reviewed date: '17/04/2017' (@ 17/04/2017) ¦ + Status changed to 'Not started' (@ 4/16/2017) ¦ + Status changed to 'Closed' (@ 4/16/2017) ¦ + Status changed to 'In progress' (@ 4/16/2017) ¦ + New reviewed date: '26/04/2017' (@ 13/04/2017) ¦ + Status changed to 'Not started' (@ 13/04/2017) ¦ + Status changed to 'Closed' (@ 13/04/2017) ¦ + Status changed to 'In progress' (@ 13/04/2017) ¦ + Status changed to 'Closed' (@ 13/04/2017) + Status changed to 'In progress' (@ 13/04/2017) + Status changed to 'Canceled' (@ 13/04/2017) + Status changed to 'Suspended' (@ 13/04/2017) + Status changed to 'In progress' (@ 13/04/2017) + Status changed to 'Not started' (@ 13/04/2017) + Status changed to 'N/A' (@ 13/04/2017)
201713 | 201713 | Y | 1 | 201713 |  | A5 | Non-US | Story 4 description | Feature 2 |  | 13 | 2017-03-30 |  | Applied | 2017-03-30 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) | Team 2
201713 |  | N | 1 | 201726 | 1 | A6 | Non-US | Story 1 description | Feature 3 |  | 0.5 | 2017-03-27 | 2017-06-25 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 3 | + New reviewed date: '25/06/2017' (@ 19/06/2017) ¦ + New reviewed date: '15/06/2017' (@ 06/06/2017) ¦
201713 | 201716 | Y | 1 | 201713 |  | A7 | Spike | Story 1 description | Feature 4 |  | 20 | 2017-03-27 |  | Closed | 2017-04-17 | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'Closed' (@ 4/17/2017) ¦ + Status changed to 'Not started' (@ 4/17/2017) ¦
201713 |  | N | 1 | 201725 | 0 | A8 | US | Story 1 description | Feature 1 |  | 2 | 2017-03-31 | 2017-06-22 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 25/04/2017 | Team 1 | + New reviewed date: '22/06/2017' (@ 19/06/2017) ¦ + New reviewed date: '09/06/2017' (@ 06/06/2017) ¦
201713 | 201713 | Y | 1 | 201713 |  | A9 | TS | Story 2 description | Feature 1 | 1 | 5 | 2017-03-30 |  | Closed | 2017-03-30 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) | Team 1
201713 |  | N | 1 | 201716 | -1 | A10 | Epic | Story 4 description | Feature 3 |  | 40 | 2017-03-30 | 2017-04-17 | In progress |  | + Do something 1 (done at date 3) => Do something 5 | Team 3 | + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201715 |  | N | 1 | 201716 | -1 | A11 | Epic | Story 4 description | Feature 2 |  | 100 | 2017-04-13 | 2017-04-17 | Not started |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2 | + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201716 |  | Y | 0 | 201716 |  | A12 | Spike | Story 4 description | Feature 2 |  | 5 | 2017-04-17 |  |  |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
201716 |  | N | 1 | 201716 | -1 | A13 | US | Story 4 description | Feature 2 |  | 20 | 2017-04-17 |  | Not started |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Not started' (@ 4/17/2017) ¦
201713 |  | N | 1 | 201713 | -1 | A14 | US | Story 1 description | Feature 1 |  | 8 | 2017-03-31 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201713 |  | N | 1 | 201713 | -1 | A15 | Non-US | Story 1 description | Feature 1 |  | 20 | 2017-03-31 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201713 | 201713 | Y | 1 | 201713 |  | A16 | TS | Story 1 description | Feature 3 |  | 20 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 3
201713 | 201713 | Y | 1 | 201713 |  | A17 | US | Story 1 description | Feature 1 |  | 40 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201714 |  | N | 1 | 201725 | 0 | A18 | Non-US | Story 1 description | Feature 1 |  | 8 | 2017-04-03 | 2017-06-21 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + New reviewed date: '21/06/2017' (@ 19/06/2017) ¦ + Status changed to 'In progress' (@ 19/06/2017) ¦
201713 |  | N | 1 | 201726 | 1 | A19 | US | Story 1 description | Feature 1 |  | 20 | 2017-03-31 | 2017-06-30 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + New reviewed date: '30/06/2017' (@ 19/06/2017) ¦
201714 |  | N | 1 | 201714 | -1 | A20 | US | Story 1 description | Feature 3 |  | 20 | 2017-04-07 |  | Not started |  | + Do something 1 (done at date 1) => Do something 2 | Team 3
201713 | 201725 | Y | 1 | 201713 |  | A21 | Epic | Story 1 description | Feature 1 |  | 100 | 2017-03-31 |  | Applied | 2017-06-19 | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'Applied' (@ 19/06/2017) ¦
201713 | 201713 |  | 0 | 201713 |  | A22 | Epic | Story 1 description | Feature 1 |  | 100 | 2017-03-31 |  | Canceled | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201713 |  | N | 1 | 201713 | -1 | A23 | US | Story 1 description | Feature 1 |  | 5 | 2017-03-31 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201713 |  | N | 1 | 201716 | -1 | A24 | US | Story 1 description | Feature 3 |  | 5 | 2017-03-31 | 2017-04-20 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 20/04/2017 | Team 3
201713 |  | N | 1 | 201713 | -1 | A25 | US | Story 1 description | Feature 1 |  | 20 | 2017-03-31 |  | Not started |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201714 | 201713 | Y | 1 | 201714 |  | A26 | Deployment Story | Story 1 description | Feature 1 |  | 40 | 2017-04-04 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201713 |  | N | 1 | 201725 | 0 | A27 | Non-US | Story 1 description | Feature 1 |  | 2 | 2017-03-31 | 2017-06-23 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + New reviewed date: '23/06/2017' (@ 19/06/2017) ¦
201713 |  | N | 1 | 201726 | 1 | A28 | Non-US | Story 1 description | Feature 1 |  | 8 | 2017-03-31 | 2017-07-01 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 12/04/2017 | Team 1 | + New reviewed date: '01/07/2017' (@ 19/06/2017) ¦ + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201713 |  | N | 1 | 201713 | -1 | A29 | Epic | Story 4 description | Feature 2 |  | 13 | 2017-03-30 |  | In progress |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
201713 | 201713 | Y | 1 | 201713 |  | A30 | Epic | Story 1 description | Feature 1 |  | 20 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201713 | 201716 | Y | 1 | 201713 |  | A31 | Deployment Story | Story 1 description | Feature 1 |  | 5 | 2017-03-31 |  | Applied | 2017-04-17 | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'Applied' (@ 4/17/2017) ¦
201718 |  | Y | 1 | 201718 |  | A32 | Spike | Story 4 description | Feature 2 |  | 100 | 2017-04-30 |  | Applied |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
|  | Y | 0 |  |  | A33 | US | Story 1 description | Feature 1 |  | 20 |  |  |  |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 05/04/2017(@ 12/04/2017) | Team 1
201719 |  | Y | 0 | 201719 |  | A34 | Deployment Story | Story 3 description | Feature 2 |  | 2 | 2017-05-12 |  |  |  | + Do something 1 (done at date 4) => Do something 5 | Team 2
201713 |  | N | 1 | 201718 | -1 | A35 | Non-US | Story 1 description | Feature 1 |  | 8 | 2017-03-31 | 2017-04-30 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 30/04/2017 (@ 12/04/2017) | Team 1
201713 |  | N | 1 | 201716 | -1 | A36 | Deployment Story | Story 1 description | Feature 1 |  | 2 | 2017-03-31 | 2017-04-17 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 13/04/2017 (@ 12/04/2017) | Team 1 | + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201718 |  | Y | 1 | 201718 |  | A37 | Non-US | Story 4 description | Feature 2 |  | 100 | 2017-04-30 |  | Applied |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
|  | Y | 0 |  |  | A38 | Epic | Story 4 description | Feature 2 |  | 100 |  |  |  |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
201713 | 201715 | N | 1 | 201713 | -1 | A39 | Spike | Story 2 description | Feature 1 | 1 | 8 | 2017-03-30 |  | In progress | 2017-04-13 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 1 | + Status changed to 'In progress' (@ 18/04/2017) ¦
|  | Y | 0 |  |  | A40
|  | Y | 0 |  |  | A41
|  | Y | 0 |  |  | A42
|  | Y | 0 |  |  | A43
|  | Y | 0 |  |  | A44
|  | Y | 0 |  |  | A45
|  | Y | 0 |  |  | A46
|  | Y | 0 |  |  | A47
|  | Y | 0 |  |  | A48
|  | Y | 0 |  |  | A49
|  | Y | 0 |  |  | A50
|  | Y | 0 |  |  | A51
|  | Y | 0 |  |  | A52
|  | Y | 0 |  |  | A53
|  | Y | 0 |  |  | A54
|  | Y | 0 |  |  | A55
|  | Y | 0 |  |  | A56
|  | Y | 0 |  |  | A57
|  | Y | 0 |  |  | A58
|  | Y | 0 |  |  | A59
|  | Y | 0 |  |  | A60
|  | Y | 0 |  |  | A61
|  | Y | 0 |  |  | A62
|  | Y | 0 |  |  | A63
|  | Y | 0 |  |  | A64
|  | Y | 0 |  |  | A65
|  | Y | 0 |  |  | A66
|  | Y | 0 |  |  | A67
|  | Y | 0 |  |  | A68
|  | Y | 0 |  |  | A69
|  | Y | 0 |  |  | A70
|  | Y | 0 |  |  | A71
|  | Y | 0 |  |  | A72
|  | Y | 0 |  |  | A73
|  | Y | 0 |  |  | A74
|  | Y | 0 |  |  | A75
|  | Y | 0 |  |  | A76
|  | Y | 0 |  |  | A77
|  | Y | 0 |  |  | A78
|  | Y | 0 |  |  | A79
|  | Y | 0 |  |  | A80
|  | Y | 0 |  |  | A81
|  | Y | 0 |  |  | A82
|  | Y | 0 |  |  | A83
|  | Y | 0 |  |  | A84
|  | Y | 0 |  |  | A85
|  | Y | 0 |  |  | A86
|  | Y | 0 |  |  | A87
|  | Y | 0 |  |  | A88
|  | Y | 0 |  |  | A89
|  | Y | 0 |  |  | A90
|  | Y | 0 |  |  | A91
|  | Y | 0 |  |  | A92
|  | Y | 0 |  |  | A93
|  | Y | 0 |  |  | A94
|  | Y | 0 |  |  | A95
|  | Y | 0 |  |  | A96
|  | Y | 0 |  |  | A97
|  | Y | 0 |  |  | A98
|  | Y | 0 |  |  | A99
|  | Y | 0 |  |  | A100
|  | Y | 0 |  |  | A101
|  | Y | 0 |  |  | A102
|  | Y | 0 |  |  | A103
|  | Y | 0 |  |  | A104
|  | Y | 0 |  |  | A105
|  | Y | 0 |  |  | A106
|  | Y | 0 |  |  | A107
|  | Y | 0 |  |  | A108
|  | Y | 0 |  |  | A109
|  | Y | 0 |  |  | A110
|  | Y | 0 |  |  | A111
|  | Y | 0 |  |  | A112
|  | Y | 0 |  |  | A113
|  | Y | 0 |  |  | A114
|  | Y | 0 |  |  | A115
|  | Y | 0 |  |  | A116
|  | Y | 0 |  |  | A117
|  | Y | 0 |  |  | A118
|  | Y | 0 |  |  | A119
|  | Y | 0 |  |  | A120
|  | Y | 0 |  |  | A121
|  | Y | 0 |  |  | A122
|  | Y | 0 |  |  | A123
|  | Y | 0 |  |  | A124
|  | Y | 0 |  |  | A125
|  | Y | 0 |  |  | A126
|  | Y | 0 |  |  | A127
|  | Y | 0 |  |  | A128
|  | Y | 0 |  |  | A129
|  | Y | 0 |  |  | A130
|  | Y | 0 |  |  | A131
|  | Y | 0 |  |  | A132
|  | Y | 0 |  |  | A133
|  | Y | 0 |  |  | A134
|  | Y | 0 |  |  | A135
|  | Y | 0 |  |  | A136
|  | Y | 0 |  |  | A137
|  | Y | 0 |  |  | A138
|  | Y | 0 |  |  | A139
|  | Y | 0 |  |  | A140
|  | Y | 0 |  |  | A141
|  | Y | 0 |  |  | A142
|  | Y | 0 |  |  | A143
|  | Y | 0 |  |  | A144
|  | Y | 0 |  |  | A145
|  | Y | 0 |  |  | A146
|  | Y | 0 |  |  | A147
|  | Y | 0 |  |  | A148
|  | Y | 0 |  |  | A149
|  | Y | 0 |  |  | A150
|  | Y | 0 |  |  | A151
|  | Y | 0 |  |  | A152
|  | Y | 0 |  |  | A153
|  | Y | 0 |  |  | A154
|  | Y | 0 |  |  | A155
|  | Y | 0 |  |  | A156
|  | Y | 0 |  |  | A157
|  | Y | 0 |  |  | A158
|  | Y | 0 |  |  | A159
|  | Y | 0 |  |  | A160
|  | Y | 0 |  |  | A161
|  | Y | 0 |  |  | A162
|  | Y | 0 |  |  | A163
|  | Y | 0 |  |  | A164
|  | Y | 0 |  |  | A165
|  | Y | 0 |  |  | A166
|  | Y | 0 |  |  | A167
|  | Y | 0 |  |  | A168
|  | Y | 0 |  |  | A169
|  | Y | 0 |  |  | A170
|  | Y | 0 |  |  | A171
|  | Y | 0 |  |  | A172
|  | Y | 0 |  |  | A173
|  | Y | 0 |  |  | A174
|  | Y | 0 |  |  | A175
|  | Y | 0 |  |  | A176
|  | Y | 0 |  |  | A177
|  | Y | 0 |  |  | A178
|  | Y | 0 |  |  | A179
|  | Y | 0 |  |  | A180
|  | Y | 0 |  |  | A181
|  | Y | 0 |  |  | A182
|  | Y | 0 |  |  | A183
|  | Y | 0 |  |  | A184
|  | Y | 0 |  |  | A185
|  | Y | 0 |  |  | A186
|  | Y | 0 |  |  | A187
|  | Y | 0 |  |  | A188
|  | Y | 0 |  |  | A189
|  | Y | 0 |  |  | A190
|  | Y | 0 |  |  | A191
|  | Y | 0 |  |  | A192
|  | Y | 0 |  |  | A193
|  | Y | 0 |  |  | A194
|  | Y | 0 |  |  | A195
|  | Y | 0 |  |  | A196
|  | Y | 0 |  |  | A197
|  | Y | 0 |  |  | A198
|  | Y | 0 |  |  | A199
|  | Y | 0 |  |  | A200
|  | Y | 0 |  |  | A201
|  | Y | 0 |  |  | A202
|  | Y | 0 |  |  | A203
|  | Y | 0 |  |  | A204
|  | Y | 0 |  |  | A205
|  | Y | 0 |  |  | A206
|  | Y | 0 |  |  | A207
|  | Y | 0 |  |  | A208
|  | Y | 0 |  |  | A209
|  | Y | 0 |  |  | A210
|  | Y | 0 |  |  | A211
|  | Y | 0 |  |  | A212
|  | Y | 0 |  |  | A213
|  | Y | 0 |  |  | A214
|  | Y | 0 |  |  | A215
|  | Y | 0 |  |  | A216
|  | Y | 0 |  |  | A217
|  | Y | 0 |  |  | A218
|  | Y | 0 |  |  | A219
|  | Y | 0 |  |  | A220
|  | Y | 0 |  |  | A221
|  | Y | 0 |  |  | A222
|  | Y | 0 |  |  | A223
|  | Y | 0 |  |  | A224
|  | Y | 0 |  |  | A225
|  | Y | 0 |  |  | A226
|  | Y | 0 |  |  | A227
|  | Y | 0 |  |  | A228
|  | Y | 0 |  |  | A229
|  | Y | 0 |  |  | A230
|  | Y | 0 |  |  | A231
|  | Y | 0 |  |  | A232
|  | Y | 0 |  |  | A233
|  | Y | 0 |  |  | A234
|  | Y | 0 |  |  | A235
|  | Y | 0 |  |  | A236
|  | Y | 0 |  |  | A237
|  | Y | 0 |  |  | A238
|  | Y | 0 |  |  | A239
|  | Y | 0 |  |  | A240
|  | Y | 0 |  |  | A241
|  | Y | 0 |  |  | A242
|  | Y | 0 |  |  | A243
|  | Y | 0 |  |  | A244
|  | Y | 0 |  |  | A245
|  | Y | 0 |  |  | A246
|  | Y | 0 |  |  | A247
|  | Y | 0 |  |  | A248
|  | Y | 0 |  |  | A249
|  | Y | 0 |  |  | A250
|  | Y | 0 |  |  | A251
|  | Y | 0 |  |  | A252
|  | Y | 0 |  |  | A253
|  | Y | 0 |  |  | A254
|  | Y | 0 |  |  | A255
|  | Y | 0 |  |  | A256
|  | Y | 0 |  |  | A257
|  | Y | 0 |  |  | A258
|  | Y | 0 |  |  | A259
|  | Y | 0 |  |  | A260
|  | Y | 0 |  |  | A261
|  | Y | 0 |  |  | A262
|  | Y | 0 |  |  | A263
|  | Y | 0 |  |  | A264
|  | Y | 0 |  |  | A265
|  | Y | 0 |  |  | A266
|  | Y | 0 |  |  | A267
|  | Y | 0 |  |  | A268
|  | Y | 0 |  |  | A269
|  | Y | 0 |  |  | A270
|  | Y | 0 |  |  | A271
|  | Y | 0 |  |  | A272
|  | Y | 0 |  |  | A273
|  | Y | 0 |  |  | A274
|  | Y | 0 |  |  | A275
|  | Y | 0 |  |  | A276
|  | Y | 0 |  |  | A277
|  | Y | 0 |  |  | A278
|  | Y | 0 |  |  | A279
|  | Y | 0 |  |  | A280
|  | Y | 0 |  |  | A281
|  | Y | 0 |  |  | A282
|  | Y | 0 |  |  | A283
|  | Y | 0 |  |  | A284
|  | Y | 0 |  |  | A285
|  | Y | 0 |  |  | A286
|  | Y | 0 |  |  | A287
|  | Y | 0 |  |  | A288
|  | Y | 0 |  |  | A289
|  | Y | 0 |  |  | A290
|  | Y | 0 |  |  | A291
|  | Y | 0 |  |  | A292
|  | Y | 0 |  |  | A293
|  | Y | 0 |  |  | A294
|  | Y | 0 |  |  | A295
|  | Y | 0 |  |  | A296
|  | Y | 0 |  |  | A297
|  | Y | 0 |  |  | A298
|  | Y | 0 |  |  | A299
|  | Y | 0 |  |  | A300
|  | Y | 0 |  |  | A301
|  | Y | 0 |  |  | A302
|  | Y | 0 |  |  | A303
|  | Y | 0 |  |  | A304
|  | Y | 0 |  |  | A305
|  | Y | 0 |  |  | A306
|  | Y | 0 |  |  | A307
|  | Y | 0 |  |  | A308
|  | Y | 0 |  |  | A309
|  | Y | 0 |  |  | A310
|  | Y | 0 |  |  | A311
|  | Y | 0 |  |  | A312
|  | Y | 0 |  |  | A313
|  | Y | 0 |  |  | A314
|  | Y | 0 |  |  | A315
|  | Y | 0 |  |  | A316
|  | Y | 0 |  |  | A317
|  | Y | 0 |  |  | A318
|  | Y | 0 |  |  | A319
|  | Y | 0 |  |  | A320
|  | Y | 0 |  |  | A321
|  | Y | 0 |  |  | A322
|  | Y | 0 |  |  | A323
|  | Y | 0 |  |  | A324
|  | Y | 0 |  |  | A325
|  | Y | 0 |  |  | A326
|  | Y | 0 |  |  | A327
|  | Y | 0 |  |  | A328
|  | Y | 0 |  |  | A329
|  | Y | 0 |  |  | A330
|  | Y | 0 |  |  | A331
|  | Y | 0 |  |  | A332
|  | Y | 0 |  |  | A333
|  | Y | 0 |  |  | A334
|  | Y | 0 |  |  | A335
|  | Y | 0 |  |  | A336
|  | Y | 0 |  |  | A337
|  | Y | 0 |  |  | A338
|  | Y | 0 |  |  | A339
|  | Y | 0 |  |  | A340
|  | Y | 0 |  |  | A341
|  | Y | 0 |  |  | A342
|  | Y | 0 |  |  | A343
|  | Y | 0 |  |  | A344
|  | Y | 0 |  |  | A345
|  | Y | 0 |  |  | A346
|  | Y | 0 |  |  | A347
|  | Y | 0 |  |  | A348
|  | Y | 0 |  |  | A349
|  | Y | 0 |  |  | A350
|  | Y | 0 |  |  | A351
|  | Y | 0 |  |  | A352
|  | Y | 0 |  |  | A353
|  | Y | 0 |  |  | A354
|  | Y | 0 |  |  | A355
|  | Y | 0 |  |  | A356
|  | Y | 0 |  |  | A357
|  | Y | 0 |  |  | A358
|  | Y | 0 |  |  | A359
|  | Y | 0 |  |  | A360
|  | Y | 0 |  |  | A361
|  | Y | 0 |  |  | A362
|  | Y | 0 |  |  | A363
|  | Y | 0 |  |  | A364
|  | Y | 0 |  |  | A365
|  | Y | 0 |  |  | A366
|  | Y | 0 |  |  | A367
|  | Y | 0 |  |  | A368
|  | Y | 0 |  |  | A369
|  | Y | 0 |  |  | A370
|  | Y | 0 |  |  | A371
|  | Y | 0 |  |  | A372
|  | Y | 0 |  |  | A373
|  | Y | 0 |  |  | A374
|  | Y | 0 |  |  | A375
|  | Y | 0 |  |  | A376
|  | Y | 0 |  |  | A377
|  | Y | 0 |  |  | A378
|  | Y | 0 |  |  | A379
|  | Y | 0 |  |  | A380
|  | Y | 0 |  |  | A381
|  | Y | 0 |  |  | A382
|  | Y | 0 |  |  | A383
|  | Y | 0 |  |  | A384
|  | Y | 0 |  |  | A385
|  | Y | 0 |  |  | A386
|  | Y | 0 |  |  | A387
|  | Y | 0 |  |  | A388
|  | Y | 0 |  |  | A389
|  | Y | 0 |  |  | A390
|  | Y | 0 |  |  | A391
|  | Y | 0 |  |  | A392
|  | Y | 0 |  |  | A393
|  | Y | 0 |  |  | A394
|  | Y | 0 |  |  | A395
|  | Y | 0 |  |  | A396
|  | Y | 0 |  |  | A397
|  | Y | 0 |  |  | A398
|  | Y | 0 |  |  | A399
|  | Y | 0 |  |  | A400
|  | Y | 0 |  |  | A401
|  | Y | 0 |  |  | A402
|  | Y | 0 |  |  | A403
|  | Y | 0 |  |  | A404
|  | Y | 0 |  |  | A405
|  | Y | 0 |  |  | A406
|  | Y | 0 |  |  | A407
|  | Y | 0 |  |  | A408
|  | Y | 0 |  |  | A409
|  | Y | 0 |  |  | A410
|  | Y | 0 |  |  | A411
|  | Y | 0 |  |  | A412
|  | Y | 0 |  |  | A413
|  | Y | 0 |  |  | A414
|  | Y | 0 |  |  | A415
|  | Y | 0 |  |  | A416
|  | Y | 0 |  |  | A417
|  | Y | 0 |  |  | A418
|  | Y | 0 |  |  | A419
|  | Y | 0 |  |  | A420
|  | Y | 0 |  |  | A421
|  | Y | 0 |  |  | A422
|  | Y | 0 |  |  | A423
|  | Y | 0 |  |  | A424
|  | Y | 0 |  |  | A425
|  | Y | 0 |  |  | A426
|  | Y | 0 |  |  | A427
|  | Y | 0 |  |  | A428
|  | Y | 0 |  |  | A429
|  | Y | 0 |  |  | A430
|  | Y | 0 |  |  | A431
|  | Y | 0 |  |  | A432
|  | Y | 0 |  |  | A433
|  | Y | 0 |  |  | A434
|  | Y | 0 |  |  | A435
|  | Y | 0 |  |  | A436
|  | Y | 0 |  |  | A437
|  | Y | 0 |  |  | A438
|  | Y | 0 |  |  | A439
|  | Y | 0 |  |  | A440
|  | Y | 0 |  |  | A441
|  | Y | 0 |  |  | A442
|  | Y | 0 |  |  | A443
|  | Y | 0 |  |  | A444
|  | Y | 0 |  |  | A445
|  | Y | 0 |  |  | A446
|  | Y | 0 |  |  | A447
|  | Y | 0 |  |  | A448
|  | Y | 0 |  |  | A449
|  | Y | 0 |  |  | A450
|  | Y | 0 |  |  | A451
|  | Y | 0 |  |  | A452
|  | Y | 0 |  |  | A453
|  | Y | 0 |  |  | A454
|  | Y | 0 |  |  | A455
|  | Y | 0 |  |  | A456
|  | Y | 0 |  |  | A457
|  | Y | 0 |  |  | A458
|  | Y | 0 |  |  | A459
|  | Y | 0 |  |  | A460
|  | Y | 0 |  |  | A461
|  | Y | 0 |  |  | A462
|  | Y | 0 |  |  | A463
|  | Y | 0 |  |  | A464
|  | Y | 0 |  |  | A465
|  | Y | 0 |  |  | A466
|  | Y | 0 |  |  | A467
|  | Y | 0 |  |  | A468
|  | Y | 0 |  |  | A469
|  | Y | 0 |  |  | A470
|  | Y | 0 |  |  | A471
|  | Y | 0 |  |  | A472
|  | Y | 0 |  |  | A473
|  | Y | 0 |  |  | A474
|  | Y | 0 |  |  | A475
|  | Y | 0 |  |  | A476
|  | Y | 0 |  |  | A477
|  | Y | 0 |  |  | A478
|  | Y | 0 |  |  | A479
|  | Y | 0 |  |  | A480
|  | Y | 0 |  |  | A481
|  | Y | 0 |  |  | A482
|  | Y | 0 |  |  | A483
|  | Y | 0 |  |  | A484
|  | Y | 0 |  |  | A485
|  | Y | 0 |  |  | A486
|  | Y | 0 |  |  | A487
|  | Y | 0 |  |  | A488
|  | Y | 0 |  |  | A489
|  | Y | 0 |  |  | A490
|  | Y | 0 |  |  | A491
|  | Y | 0 |  |  | A492
|  | Y | 0 |  |  | A493
|  | Y | 0 |  |  | A494
|  | Y | 0 |  |  | A495
|  | Y | 0 |  |  | A496
|  | Y | 0 |  |  | A497
|  | Y | 0 |  |  | A498
|  | Y | 0 |  |  | A499
|  | Y | 0 |  |  | A500
|  | Y | 0 |  |  | A501
|  | Y | 0 |  |  | A502
|  | Y | 0 |  |  | A503
|  | Y | 0 |  |  | A504
|  | Y | 0 |  |  | A505
|  | Y | 0 |  |  | A506
|  | Y | 0 |  |  | A507
|  | Y | 0 |  |  | A508
|  | Y | 0 |  |  | A509
|  | Y | 0 |  |  | A510
|  | Y | 0 |  |  | A511
|  | Y | 0 |  |  | A512
|  | Y | 0 |  |  | A513
|  | Y | 0 |  |  | A514
|  | Y | 0 |  |  | A515
|  | Y | 0 |  |  | A516
|  | Y | 0 |  |  | A517
|  | Y | 0 |  |  | A518
|  | Y | 0 |  |  | A519
|  | Y | 0 |  |  | A520
|  | Y | 0 |  |  | A521
|  | Y | 0 |  |  | A522
|  | Y | 0 |  |  | A523
|  | Y | 0 |  |  | A524
|  | Y | 0 |  |  | A525
|  | Y | 0 |  |  | A526
|  | Y | 0 |  |  | A527
|  | Y | 0 |  |  | A528
|  | Y | 0 |  |  | A529
|  | Y | 0 |  |  | A530
|  | Y | 0 |  |  | A531
|  | Y | 0 |  |  | A532
|  | Y | 0 |  |  | A533
|  | Y | 0 |  |  | A534
|  | Y | 0 |  |  | A535
|  | Y | 0 |  |  | A536
|  | Y | 0 |  |  | A537
|  | Y | 0 |  |  | A538
|  | Y | 0 |  |  | A539
|  | Y | 0 |  |  | A540
|  | Y | 0 |  |  | A541
|  | Y | 0 |  |  | A542
|  | Y | 0 |  |  | A543
|  | Y | 0 |  |  | A544
|  | Y | 0 |  |  | A545
|  | Y | 0 |  |  | A546
|  | Y | 0 |  |  | A547
|  | Y | 0 |  |  | A548
|  | Y | 0 |  |  | A549
|  | Y | 0 |  |  | A550
|  | Y | 0 |  |  | A551
|  | Y | 0 |  |  | A552
|  | Y | 0 |  |  | A553
|  | Y | 0 |  |  | A554
|  | Y | 0 |  |  | A555
|  | Y | 0 |  |  | A556
|  | Y | 0 |  |  | A557
|  | Y | 0 |  |  | A558
|  | Y | 0 |  |  | A559
|  | Y | 0 |  |  | A560
|  | Y | 0 |  |  | A561
|  | Y | 0 |  |  | A562
|  | Y | 0 |  |  | A563
|  | Y | 0 |  |  | A564
|  | Y | 0 |  |  | A565
|  | Y | 0 |  |  | A566
|  | Y | 0 |  |  | A567
|  | Y | 0 |  |  | A568
|  | Y | 0 |  |  | A569
|  | Y | 0 |  |  | A570
|  | Y | 0 |  |  | A571
|  | Y | 0 |  |  | A572
|  | Y | 0 |  |  | A573
|  | Y | 0 |  |  | A574
|  | Y | 0 |  |  | A575
|  | Y | 0 |  |  | A576
|  | Y | 0 |  |  | A577
|  | Y | 0 |  |  | A578
|  | Y | 0 |  |  | A579
|  | Y | 0 |  |  | A580
|  | Y | 0 |  |  | A581
|  | Y | 0 |  |  | A582
|  | Y | 0 |  |  | A583
|  | Y | 0 |  |  | A584
|  | Y | 0 |  |  | A585
|  | Y | 0 |  |  | A586
|  | Y | 0 |  |  | A587
|  | Y | 0 |  |  | A588
|  | Y | 0 |  |  | A589
|  | Y | 0 |  |  | A590
|  | Y | 0 |  |  | A591
|  | Y | 0 |  |  | A592
|  | Y | 0 |  |  | A593
|  | Y | 0 |  |  | A594
|  | Y | 0 |  |  | A595
|  | Y | 0 |  |  | A596
|  | Y | 0 |  |  | A597
|  | Y | 0 |  |  | A598
|  | Y | 0 |  |  | A599
|  | Y | 0 |  |  | A600
|  | Y | 0 |  |  | A601
|  | Y | 0 |  |  | A602
|  | Y | 0 |  |  | A603
|  | Y | 0 |  |  | A604
|  | Y | 0 |  |  | A605
|  | Y | 0 |  |  | A606
|  | Y | 0 |  |  | A607
|  | Y | 0 |  |  | A608
|  | Y | 0 |  |  | A609
|  | Y | 0 |  |  | A610
|  | Y | 0 |  |  | A611
|  | Y | 0 |  |  | A612
|  | Y | 0 |  |  | A613
|  | Y | 0 |  |  | A614
|  | Y | 0 |  |  | A615
|  | Y | 0 |  |  | A616
|  | Y | 0 |  |  | A617
|  | Y | 0 |  |  | A618
|  | Y | 0 |  |  | A619
|  | Y | 0 |  |  | A620
|  | Y | 0 |  |  | A621
|  | Y | 0 |  |  | A622
|  | Y | 0 |  |  | A623
|  | Y | 0 |  |  | A624
|  | Y | 0 |  |  | A625
|  | Y | 0 |  |  | A626
|  | Y | 0 |  |  | A627
|  | Y | 0 |  |  | A628
|  | Y | 0 |  |  | A629
|  | Y | 0 |  |  | A630
|  | Y | 0 |  |  | A631
|  | Y | 0 |  |  | A632
|  | Y | 0 |  |  | A633
|  | Y | 0 |  |  | A634
|  | Y | 0 |  |  | A635
|  | Y | 0 |  |  | A636
|  | Y | 0 |  |  | A637
|  | Y | 0 |  |  | A638
|  | Y | 0 |  |  | A639
|  | Y | 0 |  |  | A640
|  | Y | 0 |  |  | A641
|  | Y | 0 |  |  | A642
|  | Y | 0 |  |  | A643
|  | Y | 0 |  |  | A644
|  | Y | 0 |  |  | A645
|  | Y | 0 |  |  | A646
|  | Y | 0 |  |  | A647
|  | Y | 0 |  |  | A648
|  | Y | 0 |  |  | A649
|  | Y | 0 |  |  | A650
|  | Y | 0 |  |  | A651
|  | Y | 0 |  |  | A652
|  | Y | 0 |  |  | A653
|  | Y | 0 |  |  | A654
|  | Y | 0 |  |  | A655
|  | Y | 0 |  |  | A656
|  | Y | 0 |  |  | A657
|  | Y | 0 |  |  | A658
|  | Y | 0 |  |  | A659
|  | Y | 0 |  |  | A660
|  | Y | 0 |  |  | A661
|  | Y | 0 |  |  | A662
|  | Y | 0 |  |  | A663
|  | Y | 0 |  |  | A664
|  | Y | 0 |  |  | A665
|  | Y | 0 |  |  | A666
|  | Y | 0 |  |  | A667
|  | Y | 0 |  |  | A668
|  | Y | 0 |  |  | A669
|  | Y | 0 |  |  | A670
|  | Y | 0 |  |  | A671
|  | Y | 0 |  |  | A672
|  | Y | 0 |  |  | A673
|  | Y | 0 |  |  | A674
|  | Y | 0 |  |  | A675
|  | Y | 0 |  |  | A676
|  | Y | 0 |  |  | A677
|  | Y | 0 |  |  | A678
|  | Y | 0 |  |  | A679
|  | Y | 0 |  |  | A680
|  | Y | 0 |  |  | A681
|  | Y | 0 |  |  | A682
|  | Y | 0 |  |  | A683
|  | Y | 0 |  |  | A684
|  | Y | 0 |  |  | A685
|  | Y | 0 |  |  | A686
|  | Y | 0 |  |  | A687
|  | Y | 0 |  |  | A688
|  | Y | 0 |  |  | A689
|  | Y | 0 |  |  | A690
|  | Y | 0 |  |  | A691
|  | Y | 0 |  |  | A692
|  | Y | 0 |  |  | A693
|  | Y | 0 |  |  | A694
|  | Y | 0 |  |  | A695
|  | Y | 0 |  |  | A696
|  | Y | 0 |  |  | A697
|  | Y | 0 |  |  | A698
|  | Y | 0 |  |  | A699
|  | Y | 0 |  |  | A700
|  | Y | 0 |  |  | A701
|  | Y | 0 |  |  | A702
|  | Y | 0 |  |  | A703
|  | Y | 0 |  |  | A704
|  | Y | 0 |  |  | A705
|  | Y | 0 |  |  | A706
|  | Y | 0 |  |  | A707
|  | Y | 0 |  |  | A708
|  | Y | 0 |  |  | A709
|  | Y | 0 |  |  | A710
|  | Y | 0 |  |  | A711
|  | Y | 0 |  |  | A712
|  | Y | 0 |  |  | A713
|  | Y | 0 |  |  | A714
|  | Y | 0 |  |  | A715
|  | Y | 0 |  |  | A716
|  | Y | 0 |  |  | A717
|  | Y | 0 |  |  | A718
|  | Y | 0 |  |  | A719
|  | Y | 0 |  |  | A720
|  | Y | 0 |  |  | A721
|  | Y | 0 |  |  | A722
|  | Y | 0 |  |  | A723
|  | Y | 0 |  |  | A724
|  | Y | 0 |  |  | A725
|  | Y | 0 |  |  | A726
|  | Y | 0 |  |  | A727
|  | Y | 0 |  |  | A728
|  | Y | 0 |  |  | A729
|  | Y | 0 |  |  | A730
|  | Y | 0 |  |  | A731
|  | Y | 0 |  |  | A732
|  | Y | 0 |  |  | A733
|  | Y | 0 |  |  | A734
|  | Y | 0 |  |  | A735
|  | Y | 0 |  |  | A736
|  | Y | 0 |  |  | A737
|  | Y | 0 |  |  | A738
|  | Y | 0 |  |  | A739
|  | Y | 0 |  |  | A740
|  | Y | 0 |  |  | A741
|  | Y | 0 |  |  | A742
|  | Y | 0 |  |  | A743
|  | Y | 0 |  |  | A744
|  | Y | 0 |  |  | A745
|  | Y | 0 |  |  | A746
|  | Y | 0 |  |  | A747
|  | Y | 0 |  |  | A748
|  | Y | 0 |  |  | A749
|  | Y | 0 |  |  | A750
|  | Y | 0 |  |  | A751
|  | Y | 0 |  |  | A752
|  | Y | 0 |  |  | A753
|  | Y | 0 |  |  | A754
|  | Y | 0 |  |  | A755
|  | Y | 0 |  |  | A756
|  | Y | 0 |  |  | A757
|  | Y | 0 |  |  | A758
|  | Y | 0 |  |  | A759
|  | Y | 0 |  |  | A760
|  | Y | 0 |  |  | A761
|  | Y | 0 |  |  | A762
|  | Y | 0 |  |  | A763
|  | Y | 0 |  |  | A764
|  | Y | 0 |  |  | A765
|  | Y | 0 |  |  | A766
|  | Y | 0 |  |  | A767
|  | Y | 0 |  |  | A768
|  | Y | 0 |  |  | A769
|  | Y | 0 |  |  | A770
|  | Y | 0 |  |  | A771
|  | Y | 0 |  |  | A772
|  | Y | 0 |  |  | A773
|  | Y | 0 |  |  | A774
|  | Y | 0 |  |  | A775
|  | Y | 0 |  |  | A776
|  | Y | 0 |  |  | A777
|  | Y | 0 |  |  | A778
|  | Y | 0 |  |  | A779
|  | Y | 0 |  |  | A780
|  | Y | 0 |  |  | A781
|  | Y | 0 |  |  | A782
|  | Y | 0 |  |  | A783
|  | Y | 0 |  |  | A784
|  | Y | 0 |  |  | A785
|  | Y | 0 |  |  | A786
|  | Y | 0 |  |  | A787
|  | Y | 0 |  |  | A788
|  | Y | 0 |  |  | A789
|  | Y | 0 |  |  | A790
|  | Y | 0 |  |  | A791
|  | Y | 0 |  |  | A792
|  | Y | 0 |  |  | A793
|  | Y | 0 |  |  | A794
|  | Y | 0 |  |  | A795
|  | Y | 0 |  |  | A796
|  | Y | 0 |  |  | A797
|  | Y | 0 |  |  | A798
|  | Y | 0 |  |  | A799
|  | Y | 0 |  |  | A800
|  | Y | 0 |  |  | A801
|  | Y | 0 |  |  | A802
|  | Y | 0 |  |  | A803
|  | Y | 0 |  |  | A804
|  | Y | 0 |  |  | A805
|  | Y | 0 |  |  | A806
|  | Y | 0 |  |  | A807
|  | Y | 0 |  |  | A808
|  | Y | 0 |  |  | A809
|  | Y | 0 |  |  | A810
|  | Y | 0 |  |  | A811
|  | Y | 0 |  |  | A812
|  | Y | 0 |  |  | A813
|  | Y | 0 |  |  | A814
|  | Y | 0 |  |  | A815
|  | Y | 0 |  |  | A816
|  | Y | 0 |  |  | A817
|  | Y | 0 |  |  | A818
|  | Y | 0 |  |  | A819
|  | Y | 0 |  |  | A820
|  | Y | 0 |  |  | A821
|  | Y | 0 |  |  | A822
|  | Y | 0 |  |  | A823
|  | Y | 0 |  |  | A824
|  | Y | 0 |  |  | A825
|  | Y | 0 |  |  | A826
|  | Y | 0 |  |  | A827
|  | Y | 0 |  |  | A828
|  | Y | 0 |  |  | A829
|  | Y | 0 |  |  | A830
|  | Y | 0 |  |  | A831
|  | Y | 0 |  |  | A832
|  | Y | 0 |  |  | A833
|  | Y | 0 |  |  | A834
|  | Y | 0 |  |  | A835
|  | Y | 0 |  |  | A836
|  | Y | 0 |  |  | A837
|  | Y | 0 |  |  | A838
|  | Y | 0 |  |  | A839
|  | Y | 0 |  |  | A840
|  | Y | 0 |  |  | A841
|  | Y | 0 |  |  | A842
|  | Y | 0 |  |  | A843
|  | Y | 0 |  |  | A844
|  | Y | 0 |  |  | A845
|  | Y | 0 |  |  | A846
|  | Y | 0 |  |  | A847
|  | Y | 0 |  |  | A848
|  | Y | 0 |  |  | A849
|  | Y | 0 |  |  | A850
|  | Y | 0 |  |  | A851
|  | Y | 0 |  |  | A852
|  | Y | 0 |  |  | A853
|  | Y | 0 |  |  | A854
|  | Y | 0 |  |  | A855
|  | Y | 0 |  |  | A856
|  | Y | 0 |  |  | A857
|  | Y | 0 |  |  | A858
|  | Y | 0 |  |  | A859
|  | Y | 0 |  |  | A860
|  | Y | 0 |  |  | A861
|  | Y | 0 |  |  | A862
|  | Y | 0 |  |  | A863
|  | Y | 0 |  |  | A864
|  | Y | 0 |  |  | A865
|  | Y | 0 |  |  | A866
|  | Y | 0 |  |  | A867
|  | Y | 0 |  |  | A868
|  | Y | 0 |  |  | A869
|  | Y | 0 |  |  | A870
|  | Y | 0 |  |  | A871
|  | Y | 0 |  |  | A872
|  | Y | 0 |  |  | A873
|  | Y | 0 |  |  | A874
|  | Y | 0 |  |  | A875
|  | Y | 0 |  |  | A876
|  | Y | 0 |  |  | A877
|  | Y | 0 |  |  | A878
|  | Y | 0 |  |  | A879
|  | Y | 0 |  |  | A880
|  | Y | 0 |  |  | A881
|  | Y | 0 |  |  | A882
|  | Y | 0 |  |  | A883
|  | Y | 0 |  |  | A884
|  | Y | 0 |  |  | A885
|  | Y | 0 |  |  | A886
|  | Y | 0 |  |  | A887
|  | Y | 0 |  |  | A888
|  | Y | 0 |  |  | A889
|  | Y | 0 |  |  | A890
|  | Y | 0 |  |  | A891
|  | Y | 0 |  |  | A892
|  | Y | 0 |  |  | A893
|  | Y | 0 |  |  | A894
|  | Y | 0 |  |  | A895
|  | Y | 0 |  |  | A896
|  | Y | 0 |  |  | A897
|  | Y | 0 |  |  | A898
|  | Y | 0 |  |  | A899
|  | Y | 0 |  |  | A900
|  | Y | 0 |  |  | A901
|  | Y | 0 |  |  | A902
|  | Y | 0 |  |  | A903
|  | Y | 0 |  |  | A904
|  | Y | 0 |  |  | A905
|  | Y | 0 |  |  | A906
|  | Y | 0 |  |  | A907
|  | Y | 0 |  |  | A908
|  | Y | 0 |  |  | A909
|  | Y | 0 |  |  | A910
|  | Y | 0 |  |  | A911
|  | Y | 0 |  |  | A912
|  | Y | 0 |  |  | A913
|  | Y | 0 |  |  | A914
|  | Y | 0 |  |  | A915
|  | Y | 0 |  |  | A916
|  | Y | 0 |  |  | A917
|  | Y | 0 |  |  | A918
|  | Y | 0 |  |  | A919
|  | Y | 0 |  |  | A920
|  | Y | 0 |  |  | A921
|  | Y | 0 |  |  | A922
|  | Y | 0 |  |  | A923
|  | Y | 0 |  |  | A924
|  | Y | 0 |  |  | A925
|  | Y | 0 |  |  | A926
|  | Y | 0 |  |  | A927
|  | Y | 0 |  |  | A928
|  | Y | 0 |  |  | A929
|  | Y | 0 |  |  | A930
|  | Y | 0 |  |  | A931
|  | Y | 0 |  |  | A932
|  | Y | 0 |  |  | A933
|  | Y | 0 |  |  | A934
|  | Y | 0 |  |  | A935
|  | Y | 0 |  |  | A936
|  | Y | 0 |  |  | A937
|  | Y | 0 |  |  | A938
|  | Y | 0 |  |  | A939
|  | Y | 0 |  |  | A940
|  | Y | 0 |  |  | A941
|  | Y | 0 |  |  | A942
|  | Y | 0 |  |  | A943
|  | Y | 0 |  |  | A944
|  | Y | 0 |  |  | A945
|  | Y | 0 |  |  | A946
|  | Y | 0 |  |  | A947
|  | Y | 0 |  |  | A948
|  | Y | 0 |  |  | A949
|  | Y | 0 |  |  | A950
|  | Y | 0 |  |  | A951
|  | Y | 0 |  |  | A952
|  | Y | 0 |  |  | A953
|  | Y | 0 |  |  | A954
|  | Y | 0 |  |  | A955
|  | Y | 0 |  |  | A956
|  | Y | 0 |  |  | A957
|  | Y | 0 |  |  | A958
|  | Y | 0 |  |  | A959
|  | Y | 0 |  |  | A960
|  | Y | 0 |  |  | A961
|  | Y | 0 |  |  | A962
|  | Y | 0 |  |  | A963
|  | Y | 0 |  |  | A964
|  | Y | 0 |  |  | A965
|  | Y | 0 |  |  | A966
|  | Y | 0 |  |  | A967
|  | Y | 0 |  |  | A968
|  | Y | 0 |  |  | A969
|  | Y | 0 |  |  | A970
|  | Y | 0 |  |  | A971
|  | Y | 0 |  |  | A972
|  | Y | 0 |  |  | A973
|  | Y | 0 |  |  | A974
|  | Y | 0 |  |  | A975
|  | Y | 0 |  |  | A976
|  | Y | 0 |  |  | A977
|  | Y | 0 |  |  | A978
|  | Y | 0 |  |  | A979
|  | Y | 0 |  |  | A980
|  | Y | 0 |  |  | A981
|  | Y | 0 |  |  | A982
|  | Y | 0 |  |  | A983
|  | Y | 0 |  |  | A984
|  | Y | 0 |  |  | A985
|  | Y | 0 |  |  | A986
|  | Y | 0 |  |  | A987
|  | Y | 0 |  |  | A988
|  | Y | 0 |  |  | A989
|  | Y | 0 |  |  | A990
|  | Y | 0 |  |  | A991
|  | Y | 0 |  |  | A992
|  | Y | 0 |  |  | A993
|  | Y | 0 |  |  | A994
|  | Y | 0 |  |  | A995
|  | Y | 0 |  |  | A996
|  | Y | 0 |  |  | A997
|  | Y | 0 |  |  | A998
|  | Y | 0 |  |  | A999
Formulas:
Target Week = IF([Target Date]="","",IF(WEEKNUM([Target Date])<10,VALUE(CONCATENATE(YEAR([Target Date]),"0",WEEKNUM([Target Date]))),VALUE(CONCATENATE(YEAR([Target Date]),WEEKNUM([Target Date])))))
Week of closure or appling = IF([Closure or Applied Date]="","",IF(WEEKNUM([Closure or Applied Date])<10,VALUE(CONCATENATE(YEAR([Closure or Applied Date]),"0",WEEKNUM([Closure or Applied Date]))),VALUE(CONCATENATE(YEAR([Closure or Applied Date]),WEEKNUM([Closure or Applied Date])))))
Target Sprint / Week = IF([Date reviewed]="",[Target Week],IF(WEEKNUM([Date reviewed])<10,VALUE(CONCATENATE(YEAR([Date reviewed]),"0",WEEKNUM([Date reviewed]))),VALUE(CONCATENATE(YEAR([Date reviewed]),WEEKNUM([Date reviewed])))))

## ReleaseProgress
MONITORING PROGRESS |  | Current Sprint/Week : |  |  | 201725
Sprint / Week begin following : | 201713
StoryMapping |  | 201713 | 201714 | 201715 | 201716 | 201717 | 201718 | 201719 | 201720 | 201721 | 201722 | 201723 | 201724 | 201725 | 201726 | 201727 | 201728 | 201729 | 201730 | 201731 | 201732 | 201733 | 201734 | 201735 | 201736 | 201737 | 201738 | 201739 | 201740 | 201741 | 201742 | 201743 | 201744 | 201745 | 201746 | 201747 | 201748 | 201749 | 201750 | 201751
| Goal progress | 75.76% | 84.85% | 87.88% | 90.91% | 90.91% | 96.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Actual progress | 201713: 21.21%; 201714: 21.21%; 201715: 24.24%; 201716: 33.33%; 201717: 33.33%; 201718: 33.33%; 201719: 33.33%; 201720: 33.33%; 201721: 33.33%; 201722: 33.33%; 201723: 33.33%; 201724: 33.33%; 201725: 36.36%

## Setting
ScrumProjectsPlan V0.1.7 Hassan AFIF https://github.com/h3afif/ScrumProjectsPlan
¼ Changing bellow data don't require updating any thing in workbook
| Features/Projects | Team/Contact | Team/Contact constrains |  | Data Sheet Name:
| Feature 1 | Team 1 | Risk 1 |  | StoryMapping
| Feature 2 | Team 2 | Risk 2
| Feature 3 | Team 3 | Risk 3
| Feature 4 | Team 1 | …
| Feature 5 | Team 1
| Feature 6 | Team 3
| Feature 7 | Team 4
| Feature 8 | Team 2
| Feature 9 | Team 4
| Feature 10 | Team 1
| Feature 11 | Team 3
| Feature 12 | Team 4
| Feature 13 | Team 2
| Feature 14 | Team 4
| or | NA
| Project 1 | First Last Name 1 | Busy between time 1 and time 2
| Project 2 | First Last Name 2 | Don't disturb in day 1 of week
| Project 3 | First Last Name 3 | …
| Project 4 | First Last Name 4
| Project 5 | First Last Name 5
| Project 6 | First Last Name 6
| Project 7 | First Last Name 7
| Project 8 | First Last Name 8
| Project 9 | First Last Name 9
| Project 10 | First Last Name 10
| Project 11 | First Last Name 11
| Project 12 | First Last Name 12
| Project 13 | First Last Name 13
| Project 14 | First Last Name 14
| Project 15 | First Last Name 15
| Project 16 | First Last Name 16
| Project 17 | First Last Name 17
| Project 18 | First Last Name 18
| Project 19 | First Last Name 19
| Project 20 | First Last Name 20
| Project 21 | First Last Name 21
| Project 22 | First Last Name 22
| Project 23 | First Last Name 23
| Scrum Effort Estimations (points) using Fobonacci serie | Visual only
| 0 | 0
| 0.5 | 0.5
| 1 | 1
| 2 | 2
| 5 | 5
| 8 | 8
| 13 | 13
| 20 | 20
| 40 | 40
| 100 | 100
¼ Changing data bellow requires that you click on [UPDATE ALL conditional format.] in first sheet
<= Other Color palette to copy/paste format on "Type / Module" range
| Type / Module/Sprint/Version | Description |  | Plus claire | Claire | Foncé | Plus foncé
| US | User Story: Demonstrable working software that is valuable to the product’s end-users and can be accepted by the team’s Product Owner.
| Non-US | Non-User Story: Demonstrable working software that could not be completed within the confines of a User Story and can be verified by the team as complete.
| Spike | Spike: Information or a Decision that is required to move forward with other items within the Product Backlog and can be summarized and verified by the team. | [copy] / [special paste] if you desire it
Deployment | Deployment Story | Deployment Story: Special Story to define the last week in the Sprint. Without a Story of this type the tool can not find the sprint boundary. | <========
| TS | Technical Story: Rather than a User Story, is a Story with technical goal
| Epic | Epic: Big and Fuzzy Story to be splitted
| Issue | Issue
You can change formating on the following status to be applied later on the wool line of story/task. But only these Font properties can be applied: Bold Color ColorIndex FontStyle Italic Strikethrough Underline Then Execute [UPDATE ALL conditional format.]
Status labels ad color
Not started | Not started
In progress | In progress
Closed | Closed
Canceled | Canceled
Suspended | Suspended
Applied | Applied
N/A | N/A
|  | Stories/Tasks begin line | 12
|  | Stories/Tasks end line | 150
Priority
1
2
3
4
5
¼ Data bellow should not to be changed
Computed Sprints List
Sprint 201714
Sprint 201713
Sprint 201719
Sprint 201716
BACK LOG